# METHOD OF STATEMENT

Date: 21st Sep 2018

Description of work

To unload 1 unit machine from 1 x 20ft OT container, shift and position into customer production area at ground floor

Machine Spec

1 unit Press Brake Machine

Dim: 5220 X 2200 X 3180 mm

Wt: 13, 000 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

25/09/2018   -   10:00 am

Location of Operation

#### 39 Joo Koon Circle

Nutek Pte Ltd

Equipment Use

1 x 50 ton lorry crane

Rollers/pallet truck

Wire sling/shackle

1 x forklift

Obstacles

No obstacle on crane parking area and route to machine location

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet etc..)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of  lorry crane at beside container

- Open up container canvas using ladder

- Secure wire sling to machine hoisting point

- Hoist up machine to about 6” high

- Drive container forward for machine to go through from container door

- Swing crane and load machine onto lorry chassis

- Transport lorry to unloading area

- Hoist down machine from lorry chassis to near ground level

- Insert rollers to machine base and secured with bolts and nuts

- Shift machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Remark:

MOS subject to change by supervisor/lifting supervisor on site

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175