# METHOD OF STATEMENT

Date: 10th May 2021

Description of work

To shift out 1 unit machine with accessories from production to loading area, hoist up onto Malaysia low bed/lorry and deliver Penang

Machine Spec

Makino A77

Dim: 6430 x 3918 x 2920 mm

Wt: 18, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

12/05/21   -   assist engineer to dismantle machine parts

17/05/21   -   to shift out machine and accessories from production to loading area, hoist up onto

Malaysia low bed/lorry, secured and transport to Penang

Location of Operation

#### 51 Corporation Rd

Avitron Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 633 lorry loader

Malaysia low bed/lorry

1 x forklift

Shackle

Wire/webbing sling

Rollers/pallet truck

Hydraulic/hand jack

Canvas/metal sheet (for floor protection)

Obstacles

To clear all obstruction in way of crane parking and working area

Barricade operation area to prevent persons who are not involved enter unintentionally

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoe, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# Job Scope

- Jack up machine using hydraulic jack

- Insert rollers under machine bed

- Shift out machine from production area to loading bay

- Attached required lifting gears to crane hook and secured to rigging point of machine to be lifted

- Hoist up machine 1ft above ground to check on balancing

- After well balanced, lift up machine

- Reverse M’sia low bed to near machine

- Lower down and load machine onto low bed chassis

- Release all lifting gears from machine

- Secured machine with strapping belt prior to moving out of premise

- Transport and deliver machine to Penang

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and disposed

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175