# METHOD OF STATEMENT

Date: 14th Dec 2023

Description of work

To shift out cases from temporary location to loading area, uncrate, shift and position machine into factory premise

Machine Spec

5 cases of 1 unit 15.20.14 CMM

Case 1: 330 x 230 x 71 cm / Wt: 7, 600 kg

Case 2: 270 x 140 x 261 cm / Wt: 900 kg

Case 3: 344 x 117 x 96 cm / Wt: 400 kg

Case 4: 160 x 125 x 34 cm / Wt: 549 kg

Case 5: 62 x 32 x 35 cm / Wt: 22 kg

Date of Operation

18/12/23

Time of Operation

09:40 am

Location of Operation

21 Changi North Crescent

Windsor Airmotive Asia Pte Ltd

Equipment Use

1 x lorry loader

Wire/webbing sling

Shackle

Rollers/pallet truck

Hand jack

Obstacles

Ensure no obstacles at unloading area

Barricade operation area to prevent person who are not involved enter unintentionally

Environment

No operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman, lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

All personnel at site to ensure that risk control are known and supervisor has to ensure that risk control are in place

All our workers are fully equip with standard PPE (safety shoe, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# Job Scope

# Deploy lorry crane at designated unloading area

# To shift out case from temporary location to loading area

# Uncrate case and put aside

# Insert sling to crane hook

# Secured sling to rigging point of machine

# Hoist up and detach machine from base

# Swing crane and lower down machine to near ground level

# Insert rollers under machine bed

# Shift and transport into factory premise

# Position machine at the designated location

# Unload machine from rollers and insert levelling pad under machine bed

# Once job complete, team leader will instruct the team to perform proper housekeeping

# All debris will be clear and disposed

# Job complete

# Best Regards

# Kevin Wong / Zailani

# Eric Wong Machinery Transportation Pte Ltd

# Tel: 62824175