# METHOD OF STATEMENT

Date: 06th Feb2025

Description of work

To hoist up 2 unit machine to 4th floor through shutter door opening by using platform and mobile crane

2) To hoist/unload small machine and accessories using lorry crane and forklift, shift and position to 4th floor via cargo lift

Machine Spec

Via hoist up

1 unit Focaseiki PM1100 CNC / Wt: 6, 900 kg

1 unit YCM NXV1020A CNC / Wt: 5, 800 kg

Via cargo lift

1 unit Lathe machine

1 unit Wirecut

1 unit Seiki Milling

2 unit 7ft Lathe

1 unit Robot System

Accessories/tooling/materials/cabinet

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate 4 days job:

21/02/25 – Move in small machine to 4th floor via cargo lift

22/02/25 – Hoist up 2 unit machine

24-25/02/25 – Move in accessories to 4th floor via cargo lift

Time of Operation

Estimate:

12:00 pm

Location of Operation

#### 4 Tai Seng Drive

Nanofilm Technologies International Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 70ton mobile crane

633 lorry loader

1 x platform

Wire sling

Shackle

Rollers/pallet truck

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

PPE Required
Safety helmet

Safety shoe

Safety harness

SelfRetracting lifeline

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Deployment of mobile crane at designated location for the lift

- Set up crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- 1 x mobile crane to hoist up platform to 4th floor shutter door opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on building opening slab

- Tied back platform to a competent point and secured using 1 x mobile crane

- Use of strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Rigger to attached sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist up machine to 4th floor

- Lower down machine onto platform

- Insert rollers under machine bed

- Use manual pulley to slowly released and control moving speed of machine

- Shift out machine from platform

- Position machine at the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175