# METHOD OF STATEMENT

Date: 21st Jan 2025

Description of work

To hoist up machineries to 2nd floor through shutter door opening by using platform and mobile/lorry crane

Machine Spec

1 unit Takisawa LA200MC / Wt: 4, 000 kg

1 unit Brother S700x2 / Wt: 2, 500 kg

1 unit SV-65-65DT CNC / Wt: 3, 200 kg

2 unit SV-76S CNC / Wt: 4, 000 kg each

4 unit CNC Expect SV-110S / Wt: 7, 000 kg each

1 unit Takisawa TCN2600L8 / Wt: 3, 200 kg

1 unit SV85S Vertical Machining Center / Wt: 6, 000 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate 4 days job:

03/02/25 – lay out metal plate onto grass patch

04-07/02/25 – Hoisting of machineries

Time of Operation

09:45 am

Location of Operation

#### Jurong West St 25, Bulim Square Blk 1 #02-23/24

Cosmology

Equipment Use

1 x 50 ton mobile crane

5 x 633 lorry loader

1 x platform

Wire sling

Webbing sling

Shackle

Rollers/pallet truck

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

PPE Required
Safety helmet

Safety shoe

Safety harness

SelfRetracting lifeline

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Signalman

f. Skill Mover

# JOB SCOPE

- Deployment of mobile/lorry crane at designated location for the lift

- Set up crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- Mobile crane to hoist up platform to 2nd floor shutter door opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on building opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use of strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Rigger to attached sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist up machine to 2nd floor

- Lower down machine onto platform

- Insert rollers under machine bed

- Use manual pulley to slowly released and control moving speed of machine

- Shift out machine from platform

- Position machine at the designated location

- Repeat process till all machine have been hoist up

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175