# METHOD OF STATEMENT

Date: 03rd Nov 2025

Description of work

1) To unload 1 skid of 1 unit machine from lorry chassis to the ground using forklift, detach machine from base, transport to door entrance, shift and position to designated location using rollers

2) To shift out 1 unit machine and accessories from production to loading area, using lorry loader to hoist up and load onto lorry chassis

Machine Spec

Move in

1 unit Takisawa CNC Lathe

Dim: 510 x 229 x 220 cm / Wt: 6, 800 kg

Move out

1 unit used Emco Maxx Turn 95 CNC Lathe

Dim: 480 x 210 x 220 cm / Wt: 11, 000 kg

1 unit Chip Conveyor

1 unit SIG Gundrill

1 unit coolant

2 unit pump

1 unit controller

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

10-11/11/25

Time of Operation

09:45 am

Location of Operation

249 Jalan Boon Lay

ST Engineering Advanced Material Pte Ltd

Equipment Use

2 x 633 lorry loader

1 x 10 ton forklift

Rollers/pallet truck

Hydraulic/hand jack

Woodblock

Metal sheet/canvas (to lay out for floor protection)

Obstacles

Ensure no obstacles around operation area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry loader operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity All personnel at site to ensure that risk control are known and supervisor has to ensure that risk control are in place

All our workers are equipped with standard PPE (safety shoe, safety helmet)

M.O.M certified forklift driver

# Job Scope

# Deployment of lorry loader to site

# Using 10ton forklift to fork down skid from lorry chassis to the ground

# Forklift to fork up and detach machine from base

# Transport and unload machine at door entrance

# Using rollers to transport machine into production area at ground floor

# Position machine at the designated location

# Unload machine from rollers and insert levelling pad under machine bed

# To shift out used machine and accessories from production to loading area

# Riggers to attached sling to lorry crane hook

# Secured sling to rigging point of machine

# Hoist up machine and load onto lorry chassis

# Secured machine with strapping prior to moving out of site premise

# Once job complete, team leader will instruct the team to perform proper housekeeping

# All debris will be clear and dispose

# Job complete

# Best Regards

# Kevin Wong / Zailani

# Eric Wong Machinery Transportation Pte Ltd

# Tel: 62824175