# METHOD OF STATEMENT

Date: 23rd Oct 2020

Description of work

To hoist down 1 unit forklift, using forklift to fork down 2 case to the ground, uncrate, fork up and detach machine from base, transport to door entrance, shift and position to location using pallet truck

Machine Spec

2 cases of 1 unit Tigo SF565 CMM

Case 1: 170 x 155 x 255 cm / Wt: 1, 100 kg

Case 2: 100 x 70 x 80 cm / Wt: 80 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

01/11/20 – 30/11/20

Time of Operation

09:45 am

Location of Operation

2 Pioneer Sector 3

GE Repair Solution

Equipment Use

1 x 633 lorry loader

Wire/webbing sling

Pallet truck

1 x 3 ton battery forklift

Canvas, metal plate (to lay out for floor protection)

Obstacles

Ensure no obstacles around operation area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman, lorry loader operator and forklift driver will be involved in this operation

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity All personnel at site to ensure that risk control are known and supervisor has to ensure that risk control are in place

All our workers are equip with standard PPE (safety shoe, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# Job Scope

# Deploy lorry loader at designated unloading area

# Hoist down forklift from lorry chassis

# Using forklift to fork down case to the ground

# Uncrate case

# Forklift to fork up and detach machine from base

# Transport and unload machine at door entrance

# Using pallet truck to transport machine to location

# Position machine at the designated location

# Once job complete, team leader will instruct the team to perform proper housekeeping

# All debris will be clear and dispose

# Job complete

# Best Regards

# Zailani

# Eric Wong Machinery Transportation Pte Ltd

# Tel: 62824175