# METHOD OF STATEMENT

Date: 31st Dec 2024

Description of work

To hoist down machineries from 2nd & 3rd floor through swing gate opening by using platform, mobile/lorry crane, load onto lorry chassis and deliver to new factory

Machine Spec

Refer to attached list

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate 3-4 days job

16-17/01/25 – to shift out accessories and small to loading area via cargo lift

18-19/01/25 – to shift out and hoist down machineries

Time of Operation

09:45 am

Location of Operation

#### 198 Tuas South Ave 2, West Point Bizhub

#### Index Aerospace Pte Ltd

Equipment Use

1 x 50 ton mobile crane

4-5 x lorry crane

1 x platform

Wire sling

Webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

P.P.E Required

Safety Shoe

Safety Helmet

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Riggerman

f. Skill Mover

Job Scope

- Deployment of mobile/lorry crane at designated hoisting area

- Set up crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- Barricade off work area with safety cones, red/white tape and lifting in operation signage

- Mobile crane to hoist up platform to 2nd floor swing gate opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Tied back platform to competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Shift out machine from production into platform

- Use of manual pulley and slowly pull in machine into platform

- Riggerman to insert sling to crane hook

- Secure sling to rigging point of machine

- Mobile crane to hoist up machine from platform

- Swing crane and lower down machine to the ground

- Load machine onto lorry chassis

- Secured machine with strapping belt prior to moving out of site premise and deliver to new factory

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175