# METHOD OF STATEMENT

Date: 05th Sep 2025

Description of work

To hoist down machines from 6th floor through swing gate opening by using platform and mobile crane, load up onto lorry chassis

Machine Spec

Via hoisting

1 unit Walter CNC Grinding

Dim: 200 x 170 x 200 cm / Wt: 3, 500 kg

1 unit Walter Helitronic Power CNC

Dim: 210 x 170 x 225 cm / Wt: 4, 300 kg

Via cargo lift

1 unit Laser Marking

1 unit Heliset Uno

4 units Grinder

1 unit work table

2 units Cutter

1 unit CG

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

27/09/25 (Sat)

Time of Operation

09:30 am

Location of Operation

Blk 13 Lorong 8 Toa Payoh #06-10

First Tech Products & Tools

Equipment Use

2 x 50ton mobile crane

4-5 x 633 lorry crane

1 x working platform

Wire sling

Webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

P.P.E Required

Safety Shoe

Safety Helmet

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

b. Lorry Crane Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Deployment of 2 x mobile crane at designated hoisting area

- Set up crane with outriggers fully extended and resting on metal plate/timber mats as base plate

- Barricade off work area with safety cones, red/white tape and lifting in operation signage

- 1 x mobile crane to hoist up platform to 6th floor wall hacking opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Tied back platform to competent point and secured using 1 x mobile crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Shift out machine from production and load into platform

- Riggers to insert sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist down machine from platform to the ground

- Load up machine onto lorry chassis

- Secured with strapping belt prior to being transport out of site premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175