# METHOD OF STATEMENT

Date: 11th Sep 2024

Description of work

To hoist up 3 unit machine to 3rd floor through swing gate opening by using platform and mobile/lorry crane

Machine Spec

1 unit Okamoto ACC84 Surface Grinder

Dim: 330 x 205 x 215 cm / Wt: 3, 900 kg

1 unit Okamoto ACC64 Surface Grinder

Dim: 260 x 200 x 180 cm / Wt: 3, 000 kg

1 unit Kent Surface Grinder

Dim: 300 x 200 x 190 cm / Wt: 2, 900 kgs

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

28/09/24 (Saturday job)

Time of Operation

10:30 am

Duration of Operation

Estimate:

10:30 am   –   17:00 pm

Location of Operation

#### Blk 4010 A.M.K Ave 10 #03-03

#### Song Tat Precision Pte Ltd

Equipment Use

1 x 50 ton mobile crane

2-3 x lorry loader

1 x platform

Wire sling

Webbing sling

Shackle

Rollers/pallet truck

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

P.P.E Required

Safety Shoe

Safety Helmet

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Deployment of mobile/lorry crane at designated hoisting area

- Set up crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- To barricade off work area with safety cones/red/white tape and lifting in operation signage

- Mobile crane to hoist up platform to 3rd floor swing gate opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Tied back platform to competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Riggers to insert sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist up machine to 3rd floor

- Lower down machine onto platform

- Insert pallet truck under machine bed

- Use of manual pulley to slowly release and control moving speed of machine

- Shift out machine from platform

- Position machine into customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175