# METHOD OF STATEMENT

Date: 15th Jan 2024

Description of work

1) To hoist down 1 unit machine from 2nd floor through wall hacking opening and load onto lorry chassis, transport to loading bay, hoist up to 4th floor through swing gate opening by using platform and mobile/lorry crane

2) To hoist down 1 unit machine from 4th floor through swing gate opening and load up onto lorry

3) To hoist down 1 unit machine from 5th floor through swing gate opening and load up onto lorry

Machine Spec

From #02-04 to #04-06

1 unit Akira V5-5 CNC Machining Center

Dim: 330 x 215 x 280 cm / Wt: 8, 400 kgs

Hoist down from #04-06

1 unit ESG 1632 machine

Dim: 270 x 170 x 190 cm / Wt: 3, 400 kg

Hoist down from #05-06

1 unit Akira Seiki A-500T

Dim: 230 x 150 x 210 cm / Wt: 4, 200 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

20/01/24 (Saturday job)

Time of Operation

09:30 am

Duration of Operation

09:30 am   –   18:00 pm

Location of Operation

#### Blk 5000 A.M.K Ave 5 #02-04, #04-06 & #05-06

#### Fastrack Pte Ltd

Equipment Use

2 x 50 ton mobile crane

3-4 x lorry loader

1 x platform

Wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

P.P.E Required

Safety Shoe

Safety Helmet

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile/lorry crane at designated hoisting area

- Mobile crane to hoist up platform to 2nd floor wall hacking opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Tied back platform to competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Shift out machine from production into platform

- Use of manual pulley to slowly release and control moving speed of machine

- Mobile crane to hoist down machine from 2nd floor

- To hoist machine back up to 5th floor

- Shift out machine from platform and position at the designated location

- To hoist down 1 unit machine from 4th floor and 1 unit machine from 5th floor to the ground

- Load machine onto lorry chassis and secured with strapping belt

- Transport out and deliver machine to another location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175