# METHOD OF STATEMENT

Date: 24th Nov 2023

Description of work

To hoist up 1 unit new machine to 5th floor through wall hacking/swing gate opening by using platform and mobile/lorry crane

Machine Spec

1 unit Mazak Integrex J-200

Dim: 2420 x 2990 x 2400 mm

Wt: 7, 400 kgs

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate:

16/12/23 (Saturday job)

Time of Operation

09:30 am

Duration of Operation

09:30 am   –   18:00 pm

Location of Operation

#### Blk 5012 A.M.K Ave 5 #05-01

#### Yong Chang Mould Engineering Pte Ltd

Equipment Use

1 x 50 ton mobile crane

2 x lorry loader

1 x platform

Wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

P.P.E Required

Safety Shoe

Safety Helmet

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deployment of mobile/lorry crane at designated hoisting area

- Hoist down case from low bed to the ground

- Uncrate case and put aside

- Mobile crane to hoist up platform to 5th floor wall hacking opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the building opening slab

- Tied back platform to competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Mobile crane to hoist up machine to 5th floor

- Lower down machine onto platform

- Insert rollers under machine bed

- Use of manual pulley to slowly release and control moving speed of machine

- Shift out machine from platform

- Position machine into customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175