# METHOD OF STATEMENT

Date: 07th Nov 2022

Description of Work

To unload 2 case of 1 set machine from cometto trailer at outside factory using hydraulic gantry crane, uncrate, transport to inside factory, lower down into foundation hole by using hydraulic gantry crane

Machine Spec

UKL-600M Press machine

Case 1: 4.7m x .8m x 3.4m / Wt: 65, 000 kg

Case 2: 4.45m x 3.1m x 2.95m / Wt: 37, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

11/11/22

Time of Operation

09:45 am

Location of Operation

70 Joo Koon Circle

Nakano Metal Press Pte Ltd

Equipment Use

2 set hydraulic gantry crane

633 lorry crane

Low-loader

Comentto trailer

1 x forklift

1 x boom/scissor lift

Electric/air rollers

Wire sling

4 pcs 55ton shackle

4 pcs 25ton shackle

4 pcs webbing sling (SWL: 35ton each)

Hard wooden block

Obstacles

No obstacles on operation area and route to machine position

Barricade off operation area to prevent person who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Safety Aspect

Assignment of traffic controller to guide and control movement of vehicle or personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- To unload 2 set of gantry crane from low loader using lorry crane

- To assembly gantry crane outside factory premise

- Reverse cometto trailer to near gantry crane

- Lifting personnel will attached all required lifting gears onto gantry crane which is to be secure to the load to be lifted

- Once rigging is complete, gantry crane to lift up case from cometto trailer

- Move out cometto trailer

- Lower down case to the ground

- Uncrate case and put aside

- Lifting personnel will attached all required lifting gears onto gantry crane and secure to rigging point of machine

- Lift up and detach machine from base

- Lower down machine to near ground level and insert rollers under machine bed

- Transport machine into factory premise

- Dismantle gantry crane

- Shift gantry into inside factory and position to location

- Assembly gantry crane

- Gantry crane to lift up machine and lower down slowly into foundation hole

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani / Kevin Wong

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175