# METHOD OF STATEMENT

Date: 28th Dec 2020

Description of Work

To unload 1 set of machine from cometto trailer at outside factory, transport to inside factory using auto control cometto, lower down into hole by using hydraulic gantry crane

Machine Spec

1 unit Aida Progmax Press / PMX-S2-12000

Refer to packing list attached

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate: 02/01/2021

Time of Operation

10:00 am

Location of Operation

20 Benoi Sector

Shimano (S) Pte Ltd

Equipment Use

2 set hydraulic gantry crane

633 lorry crane

Low-loader

Comentto trailer

15m auto control cometto

1 x forklift

Wire sling

4 pcs 55ton shackle

4 pcs 85ton shackle

4 pcs 20ton shackle

4 x 3m webbing sling (SWL: 50ton each)

Hard wooden block

Factory overhead crane

Obstacles

No obstacles on operation area and route to machine position

Barricade off operation area to prevent person who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Safety Aspect

Assignment of traffic controller to guide and control movement of vehicle or personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- To unload 2 set of gantry crane from low loader using lorry crane

- To assembly gantry crane outside factory premise

- Transport cometto trailer to near gantry crane

- Lifting personnel will attached all required lifting gears onto gantry crane which is to be secure to the load to be lifted

- Once rigging is complete, gantry crane to lift up machine from cometto trailer

- Move out cometto trailer and transfer machine onto 15m auto control cometto

- Reverse cometto into inside factory building

- Dismantle gantry crane

- Shift gantry into inside factory and position to location

- Assembly gantry crane by using factory overhead crane

- Lift up machine from cometto

- Lower down machine slowly into foundation hole

- Repeat process till all machine and parts are position at the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175