# METHOD OF STATEMENT

Date: 17th Mar 2022

Description of Work

To dismantle 1 unit press machine into parts using hydraulic gantry crane, shift out to outside factory, using mobile crane to hoist up machine onto low loader/cometto trailer, transport and deliver to new factory

Machine Spec

1unit CF1-630 Press

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

Estimate:

31/03/22 – 30/04/22

Time of Operation

09:45 am

Location of Operation

Shimano (S) Pte Ltd

20 Benoi Sector – 11 Bulim Walk

Equipment Use

2 set hydraulic gantry crane

1 x 160 ton mobile crane

Low-loader/c

Cometto trailer

1 x 4.5ton forklift

Wire sling

4 pcs 55ton shackle

4 pcs 25ton shackle

Hard wooden block

Obstacles

No obstacles on operation area and route to machine position

Barricade off operation area to prevent person who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose after job completion

Safety Aspect

Assignment of traffic controller to guide and control movement of vehicle or personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- To unload 2 set of gantry crane from low loader using lorry crane

- Shift gantry crane into factory premise

- To assembly gantry crane inside factory

- Lifting personnel will attached all required lifting gears onto gantry crane which is to be secure to the load to be lifted

- Once rigging is complete, gantry crane to lift up machine by parts

- Shift out gantry crane

- Lower down machine to near ground level

- Insert rollers under machine bed

- Shift out to loading area

- Mobile crane to hoist up machine and load onto low-loader/cometto trailer

- Secure machine with chain lock

- Transport and deliver machine to new factory

- Unload into foundation hole using mobile crane

- Repeat process till all machine parts are assemble

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani / Kevin Wong

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175