# METHOD OF STATEMENT

Date: 27th Dec 2021

Description of Work

To shift out and lay down 2 unit press machine using hydraulic gantry crane, transport to outside factory, using mobile crane to hoist up machine onto low loader, transport to new factory, unload, shift and position to location

Machine Spec

2 unit Ching Fong Press (No 655, 653)

Dim: 3391 x 3200 x 6628

Est Wt: 55, 000 kg

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

05/01/22 – 05/03/22

Estimate 2 month job

Time of Operation

09:45 am

Location of Operation

20 Benoi Sector

Shimano (S) Pte Ltd

Equipment Use

2 set hydraulic gantry crane

1 x 160 ton mobile crane

Low-loader

1 x 4.5ton forklift

Wire sling

4 pcs 55ton shackle

4 pcs 85ton shackle

4 x 3m webbing sling (SWL: 50ton each)

Hard wooden block

Chain block

Obstacles

No obstacles on operation area and route to machine position

Barricade off operation area to prevent person who are not involved enter unintentionally

Environment

No operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose after job completion

Safety Aspect

Assignment of traffic controller to guide and control movement of vehicle or personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- To unload 2 set of gantry crane from low loader using lorry crane

- Shift gantry crane into factory premise

- To assemble gantry crane near machine

- Lifting personnel will attached all required lifting gears onto gantry crane which is to be secure to the load to be lifted

- Once rigging is complete, gantry crane to lift up machine from foundation hole

- Shift gantry crane away from foundation hole

- Lay down machine

- Shift out machine to loading area

- Mobile crane to hoist up machine and load onto low loader

- Secured machine with chain lock

- Transport and deliver to new factory

- Unload and transport machine into factory premise

- Using gantry crane to upright and lower down machine onto foundation hole

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175