# METHOD OF STATEMENT

Date: 30th Mar 2022

Description of work

To shift out and hoist down 3 unit machine from 4th floor by using platform and mobile/lorry crane, load onto lorry chassis and deliver to new location

Machine Spec

1 unit Litz800 CNC

Dim: 200 x 220 x 260 cm / Wt: 5, 000 kg

1 unit Litz CV800

Dim: 200 x 220 x 260 cm / Wt: 5, 500 kg

1 unit Fanuc

Dim: 229 x 185 x 225 / Wt: 1, 990 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

07/04/22 (Thursday)

Time of Operation

09:45 am

Location of Operation

53 Serangoon North Ave 4 #03-04A

Mieux Pte Ltd

Equipment Use

1 x 70 ton mobile crane

1 x 633 FALFINGER lorry loader

2 x lorry crane

1 x platform

1 set wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose.

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

P.P.E Required

Safety helmet

Safety shoe

Safety harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                           Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile/lorry crane at designated hoisting area for the lift

- Mobile crane to hoist up platform to 4th floor gate opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on building opening slab

- Tied back platform to a competent point and secured using 1 x lorry loader

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Shift out machine from production and load onto platform

- Insert sling to crane hook and secure onto machine hoisting point

- Hoist up machine slowly to check on balancing

- When all are balance well, mobile crane to hoist and lower down machine to the ground

- Load machine onto lorry chassis

- Secured machine with strapping belt prior to moving out of premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani / Kevin Wong

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175