# METHOD OF STATEMENT

Date: 26th Nov 2024

Description of work

To hoist down machineries from 2nd floor through shutter door opening by using platform and mobile/lorry crane, load onto wooden base for packing, after packing load onto customer arrange container

Machine Spec

Refer to list attached

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate:

29/11/24 – to shift out accessories for packing

02-07/12/24 – to hoist down machineries from 2nd floor for packing, after packing load up onto

container

Time of Operation

09:45 am

Location of Operation

#### 51 Marsiling Rd

Beyonics International Pte Ltd

Equipment Use

1 x 50 ton mobile crane

2 x 633 lorry loader

1 x platform

1 set wire sling

Webbing sling

Shackle

Canvas/metal plate (to lay out for floor protection)

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose.

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness) Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile/lorry crane at designated hoisting area for the lift

- Mobile crane to hoist up platform to 2nd floor shutter door opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Shift out machine from production

- Load machine onto platform

- Use of manual pulley to slowly release and control moving speed of machine

- Rigger to attached sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist down machine to the ground

- Load up machine onto wooden base

- Pack to form a case

- After packing to load up onto customer arrange container

- Secured case with chocking wood and lashing belt

- Once job done, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175