# METHOD OF STATEMENT

Date: 21st Nov 2024

Description of work

1) To hoist down 1 unit machine from 4th floor through wall hacking opening by using platform and lorry crane

2) To hoist up 1 unit machine to 4th floor through wall hacking opening by using platform and lorry crane

Machine Spec

Hoist down

1 unit ESG-1224ASD machine

Dim: 245 x 212 x 211 cm

Wt: 2, 200 kg

Hoist up

1 unit PFG-CL3060AH Grinder machine

Dim: 265 x 155 x 180 cm

Wt: 1, 700 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

06/12/24 (Friday

Time of Operation

10:00 am

Location of Operation

Alcotec Precision Engineering Pte Ltd

#### Blk 31 Defu Lane 10 #04-72

Equipment Use

2 x 633 lorry loader

1 x platform

1 set wire sling

Webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade off operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation

P.P.E Required

Safety Helmet

Safety Shoe

Safety Harness

Self Retracting Lifeline

Safety Aspect

1) Barricade off work area with safety cones, red/white tape and lifting in operation signage

2) All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            3) Lifting machine and lifting gear with M.O.M certificate

4) Lifting crew shall be composed to the following but not limited by other trained personnel in       respect to the number of crew needed for the operation:

a. Lifting Supervisor

b. Lorry Loader Operator

d. Riggerman

e. Signalman

f. Skill Mover

# JOB SCOPE

- Deployment of 2 x lorry crane at designated hoisting area for the lift

- Setting up of crane with outriggers fully extended and resting on steel plate/timber mats with appropriate dimension

- 1 x lorry crane to hoist up platform to 4th floor wall hacking opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform to building railing/pillar to prevent platform swing outward

- Shift out machine from production to near platform

- Use manual pulley to slowly pull in machine into platform

- Rigger to insert sling to crane hook

- Secured sling to rigging point of machine

- 1 x lorry crane to hoist up machine from platform

- Swing crane and lower down machine to the ground

- Load up machine onto lorry chassis

- To hoist up new machine to 4th floor

- Shift and position into tenant premise

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175