# METHOD OF STATEMENT

Date: 26th July 2023

Description of work

To hoist up 5 unit machine to 3rd floor through shutter door opening by using platform and mobile/lorry crane

Machine Spec

Vertical CNC / CMX-800V

Dim: 3500 x 2300 x 2550 mm

Wt: 5, 250 kg each

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

01/08/23 (Tuesday)

Time of Operation

09:45 am

Location of Operation

#### 3 Toh Guan Rd East 3rd Level

Knight Auto Precision Engineering Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 633 FALFINGER lorry loader

3-4 x lorry crane

1 x platform

1 set wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose.

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness) Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile/lorry crane at designated hoisting area for the lift

- Mobile crane to hoist up platform to 3rd floor shutter door opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on building opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform onto building railing/pillar to prevent platform swing outward

- Insert sling to crane hook and secure onto machine rigging point

- Mobile crane to hoist up machine to 3rd floor

- Lower down machine onto platform

- Insert rollers/pallet truck under machine base

- Use of manual pulley to slowly release and control moving speed of machine

- Shift out machine from platform

- Position machine to the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175