# METHOD OF STATEMENT

Date: 02nd Dec 2021

Description of work

To hoist up 1 unit machine to 3rd floor through swing gate opening by using platform and mobile/lorry crane

Machine Spec

Tsugami CNC Lathe

Dim: 245 x 185 x 193 cm

Wt: 5, 500 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

16/12/21 (Thursday)

Time of Operation

09:40 am

Duration of Operation

09:40am – 13:00 pm

Location of Operation

#### 53 Serangoon North Ave 4 #03-04A

Mieux Pte Ltd

Equipment Use

1 x PALFINGER PK110002SHH lorry loader

2 x lorry crane

1 x platform

1 set wire sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

P.P.E Required

Safety Helmet

Safety Shoe

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- 2 x lorry crane to be deploy at designated hoisting area for the lift

- Hoist up platform to 3rd floor gate opening

- Stabilize platform effectively and ensure platform 3ft metal plate protruding is fully lean and rested on the opening slab

- Tied back platform to a competent point and secured using 1 x lorry crane

- Use strong belt to secure front left and right of platform to building railing/pillar to prevent platform swing outward

- 1 x lorry crane to hoist up machine to 3rd floor

- Lower down machine onto platform

- Insert rollers/pallet truck to machine base

- Shift out machine from platform

- Position machine to the designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani / Kevin Wong

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175