# METHOD OF STATEMENT

Date: 11th Oct 2019

Description of work

To unload and hoist down 7 cases of 1 unit machine from low loader, uncrate, upright machine and hoist up onto cometto, reverse to loading bay, insert rollers to machine base, shift and position into production area at ground floor

Machine Spec

1 unit Aida 300 ton Press

Case 1: 487 x 391 x 380 cm / Wt: 46, 000 kgs

Case 2: 170 x 160 x 200 cm / Wt: 1, 200 kgs

Case 3: 160 x 150 x 180 cm / Wt: 500 kg

Case 4: 150 x 100 x 200 cm / Wt: 500 kgs

Case 5: 140 x 100 x 90 cm / Wt: 900 kgs

Case 6: 315 x 122 x 100 cm / Wt: 900 kgs

Case 7: 410 x 270 x 30 cm / Wt: 4, 100 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

19/10/2019

Time of Operation

09:45 am

Location of Operation

#### 51 Marsiling Rd

Beyonics International Pte Ltd

Equipment Use

1 x 200 ton mobile crane

1 x 633 lorry loader

1 x cometto

Heavy duty rollers/pallet truck

1 set wire

Shackle

Obstacles

No obstacle on crane and unloading area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation

Safety Aspect

Assignment of traffic controller to control movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy mobile/lorry crane at designated unloading area

- Hoist down cases from low loader

- Uncrate case

- Hoist up and upright machine

- Load machine onto cometto

- Reverse cometto to loading bay

- Jack up machine

- Insert rollers under machine base

- Shift out machine cometto into production area at ground floor

- Position machine at the designated location

- Unload machine from rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175