# METHOD OF STATEMENT

Date: 24th Sep 2020

Description of work

To unload 3 unit machine and accessories from customer arranged container, shift and position into factory premise at ground floor

Machine Spec

2 unit used Mori Seiki CNC Lathe

Dim: 620 x 350 x 320 cm

Wt: 18, 500 kg

1 used CMM machine

Dim: 364 x 254 x 278 cm

Wt: 6, 500 kg

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

26/09/20 – 03/10/20

Time of Operation

10:00 am

Location of Operation

#### 127 Pioneer Rd

Fong Lee Metal Industries Pte Ltd

Equipment Use

1 x 70 ton mobile crane

2 x 633 lorry loader

Heavy duty rollers

1 set wire/webbing sling

Shackle

Metal sheet/canvas (for epoxy floor protection)

1 x forklift

Obstacles

No obstacle on crane parking area and route to machine position

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of mobile crane at designated location

- Insert wire sling under machine case

- Hoist up machine case to check on balancing

- When well balancing, hoist down machine case from container

- Unload case to the ground

- Uncrate case

- After uncrate, hoist machine and detach from base

- Swing machine away from base

- Lower down machine slowly to near ground level

- Insert heavy duty rollers to machine base and secured with bolts and nuts

- Transport machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175