# METHOD OF STATEMENT

Date: 03rd Nov 2020

Description of work

To unload 2 unit machine with accessories from low loader/lorry chassis, shift and position into factory premise at ground floor

Machine Spec

1 unit Mazak NEXUS 5000

Dim: 490 x 280 x 280 cm / Wt: 12, 000 kgs

1 unit Mazak MTV815/80

Dim: 640 x 370 x 380 cm / Wt: 14, 000 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

09/11/20

Location of Operation

#### No 16 Seletar Aerospace Crescent

JEP Precision Engineering Pte Ltd

Equipment Use

1 x 633 lorry loader – PALFINGER PK 100002E

1 x lorry loader

1 x low-loader

1 x forklift

Heavy duty rollers/pallet truck

1 set wire/webbing sling

Metal plate/canvas (for epoxy floor protection)

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

Barricade off work area with safety cones, red/white tape and lifting in operation signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Deploy lorry loader at unloading area

- Reverse low loader to near crane

- Hoist up machine from low loader and lower down to near ground level

- Swing crane to unloading area

- Insert rollers to machine base

- Use of forklift to assist in pulling/pushing to transport machine into production

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175