# METHOD OF STATEMENT

Date: 08th Nov 2018

Description of work

To unload 1 unit Brown & Sharp CMM, 1 unit OKUMA MA-50HB and accessories from low bed/lorry chassis, shift and position into customer premise

Machine Spec

1 unit OKUMA MA-50HB

Dim: 420 x 270 x 330 cm

Wt: 21, 000 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

09/11/2018 – To unload and position CMM and accessories

12/11/2018 – To unload, shift and position OKUMA MA-50HB

Location of Operation

#### No 16 Seletar Aerospace Crescent

JEP Precision Engineering Pte Ltd

Equipment Use

1 x 70 ton mobile crane

2 x lorry crane

1 x low bed

1 x forklift

Heavy duty rollers/pallet truck

Metal plate/canvas (for epoxy floor protection)

Wire/webbing sling

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet etc..)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Park low bed/lorry at designated location

- Using forklift/lorry crane to unload machine parts and accessary and put aside

- 70 ton mobile crane to hoist down machine from low bed chassis and lower down to near ground level

- Swing crane to unloading area

- Insert rollers to machine base

- Transport machine into production room

- Shift and position at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Shift machine parts and accessary to near machine for engineer to assemble

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris, if any will be clear and dispose

- Job complete

Remark:

MOS subject to change by supervisor/lifting supervisor on site

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175