# METHOD OF STATEMENT

Date: 20 Nov 2015

Description of work

To hoist up 1 unit CNC machine to 4th level, shift and position into customer premise

Machine Spec

1 unit HwaCheon CNC Lathe M/Cutex-160A

Dim: 384 x 218 x 216 cm

Wt: 4,040 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

24/11/2015 - 09:30am

Location of Operation

#### Blk 113 Defu Lane 10 #04

Dou Yee Technologies Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 50 ton lorry crane

1 x platform

Wire sling

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

MOM certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crew certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, helmet, safety harness etc..) Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by MOM certified lifting supervisor, rigger and signalman.

# JOB SCOPE

- Mobile/lorry crane to park at designated hoisting area for the lift

- Hoist up platform to 4th level opening

- Stabilize platform effectively and ensure it is fully rested on the opening slab

- Tied back platform to a competent point and secured using 50 ton lorry crane

- Use strong belt to secure front left and right of platform to prevent platform swing outward

- 50 ton mobile crane to hoist up machine to 4th floor

- Lower down machine slowly onto platform

- Insert rollers/pallet truck to machine base

- Shift out machine from platform and position into customer premise

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175