# METHOD OF STATEMENT

Date: 21st Oct 2024

Description of work

1) To hoist down 3 unit machine from 4th floor through wall hacking opening by using platform and mobile/lorry crane

2) To hoist down 1 unit machine from 4th floor to 3rd floor through wall hacking opening by using platform and mobile/lorry crane

3) To shift out 4 unit small machine from 4th floor to 3rd floor via cargo lift

Risk Assessment

A copy of Risk Assessment will be attach

Date of Operation

2-3 day job (Fri, Sat & Sun)

08/11/24  –  (Shift out machine from 4th floor to 3rd floor via cargo lift)

09/11/24  –  10/11/24 (Hoisting of machineries)

Time of Operation

10:00 am

Location of Operation

#### Swift Silicone Pte Ltd

#### Blk 30 Loyang Way #04-01

Equipment Use

1 x 50 ton mobile crane

1 x 633 lorry crane

3-4 x lorry

1 x platform

Rollers/pallet truck

Wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carry out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

P.P.E Required

Safety Helmet

Safety Shoe

Safety Harness

Self Retracting Lifeline

Safety Aspect

Assignment of traffic controller to control and guide movement of vehicle and personnel within the vicinity

Barricade off work area with safety cones, red/white tape and lifting in progress signage

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)

Lifting machine and lifting gear with M.O.M certificate

Lifting crew shall be composed to the following but not limited by other trained personnel in respect to number of crew needed for the operation:

a. Lifting Supervisor

b. Mobile Crane Operator

c. Lorry Loader Operator

d. Signalman

e. Riggerman

f. Skill Mover

# JOB SCOPE

- Deployment of mobile/lorry crane at designated hoisting area for the lift

- Setting up of crane with outriggers fully extended and resting on steel plate/timber mats as base plate

- Mobile crane to hoist up platform to 4th level wall hacking opening

- Stabilize platform effectively and ensure platform 3ft metal protruding is fully lean and rested on the opening slab

- Tied back platform to a competent point and secured using 1 x 50 ton lorry crane

- Use strong belt to secure front left and right of platform to building railing/pillar to prevent platform swing outward

- To shift out machine from production to near platform

- Use manual pulley to slowly pull in machine into platform

- Riggers to insert sling to crane hook

- Secured sling to rigging point of machine

- Mobile crane to hoist up machine from platform

- Swing crane and lower down machine to the ground

- Load up machine onto lorry chassis

- Transport and deliver to new location

- Once job complete, team leader will instruct the team to perform proper housekeeping

- All debris will be clear and dispose

- Job complete

Best Regards

Kevin Wong / Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175