# METHOD OF STATEMENT

Date: 24th Apr 2018

Description of work

To unload 6 cases of 1 unit machine from 1 x 40ft FR, 1 x 40ft GP and 1 x 40ft HQ container, uncrate, shift and position into showroom

Machine Spec

Horizontal Y-Axis Control CNC Lathe Integrex I-300S

Main Machine Dim: 6.950 x 3.060 x 3.400 m

G/Wt: 17, 980 kgs

N/Wt: 16, 150 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

27/04/2018   -    09:45 am

Location of Operation

#### No 21 Joo Koon Circle

Yamazaki Mazak Singapore Pte Ltd

Equipment Use

1 x 50 ton mobile crane

1 x 50 ton lorry crane

1 x low loader

Wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, helmet etc..)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of mobile crane at location

- Hoist up machine case from FR container and load onto ground

- Uncrate case

- Hoist up and detach machine from base

- Load machine onto low loader

- Reverse low loader to inside factory

- Using customer overhead crane to unload machine from low loader

- Shift and position machine to designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175