# METHOD OF STATEMENT

Date: 20th Nov 2018

Description of work

To unload 2 cases of 1 unit machine from 1 x 20ft GP and 1 x 40ft FR container, uncrate, shift and position into showroom

Machine Spec

Optiplex Nexus 3015 Fiber Laser Cutting

Case 1: 8.39 m x 3.24 m x 3.14 m   /   Wt: 12, 770 kgs

Case 2: 5.02 m x 2.29 m x 1.99 m   /   Wt: 4, 460 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

21/11/2018   -   Unload from container and put aside

22/11/2018   -   Uncrate, shift and position into showroom

Location of Operation

#### No 21 Joo Koon Circle

Yamazaki Mazak Singapore Pte Ltd

Equipment Use

1 x 50 ton lorry crane

1 x low loader

Wire/webbing sling

Shackle

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and disposed

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of lorry crane at designated location

- Hoist down case from FR container to the ground

- Uncrate case

- Hoist and detach machine from base

- Load machine onto low loader chassis

- Reverse low loader to inside factory

- Using customer overhead crane to unload machine from lorry chassis

- Shift and position machine to designated location

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Remark:

MOS subject to change by supervisor/lifting supervisor on site

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175