# METHOD OF STATEMENT

Date: 11th June 2019

Description of work

To unload 10 cases of 1 unit machine from 2 x 40ft FR and 2 x 40ft HQ container, uncrate, shift and position into customer premise at ground floor

Machine Spec

10 cases of 1 unit CNC Machining Center N30MC/1500

Case 1: 840 x 359 x 392 cm      N/G Wt: 25, 955 kgs / 31, 400 kgs

Case 2: 294 x 276 x 300 cm      N/G Wt: 1, 235 kgs / 2, 335 kgs

Case 3: 360 x 148 x 250 cm      N/G Wt: 435 kgs / 1, 195 kgs

Case 4: 133 x 80 x 205 cm        N/G Wt: 144 kgs / 340 kgs

Case 5: 360 x 100 x 92 cm        N/G Wt: 406 kgs / 720 kgs

Case 6: 996 x 230 x 229 cm      N/G Wt: 1, 487 kgs / 2, 870 kgs

Case 7: 230 x 230 x 48 cm        N/G Wt: 390 kgs / 725 kgs

Case 8: 384 x 176 x 290 cm      N/G Wt: 1, 288 kgs / 2, 215 kgs

Case 9: 230 x 108 x 127 cm      N/G Wt: 200 kgs / 490 kgs

Case 10: 375 x 286 x 385 cm    N/G Wt: 4, 305 kgs / 5, 850 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date of Operation

Estimate: 17-21/06/2019

Time of Operation

09:45 am

Location of Operation

#### No 51 Seletar Aerospace View

Pratt & Whitney NGPF Manufacturing Company Pte Ltd

Equipment Use

1 x 70 ton mobile crane

1 x 50 ton mobile crane

Lorry crane

Heavy duty rollers

1 set wire/webbing sling

Shackle

Metal sheet/canvas (for epoxy floor protection)

1 x 3 ton battery forklift

1 x boom lift

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of 2 x mobile crane at designated location

- Insert wire sling under machine case

- Using 1 x 70ton and 1 x 50ton mobile crane to slowly hoist up machine case

- After balancing had been achieved, hoist down machine case from FR container

- Unload case to the ground

- Uncrate case with the use of boom/scissor lifter

- After uncrate, hoist machine and detach from base

- Shift machine base away using forklift

- Lower down machine slowly to near ground level

- Insert heavy duty rollers to machine base and secured with bolts and nuts

- Transport machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175