# METHOD OF STATEMENT

Date: 07th August 2018

Description of work

To unload 12 cases of 1 unit machine from Schenker arranged container, uncrate, shift and position into customer premise at ground floor

Machine Spec

12 cases of 1 unit N30/4MC Machine

Case 1: 1462 x 372 x 394 cm    N/G Wt: 47, 000 kgs / 55, 693 kgs

Case 2: 1379 x 160 x 249 cm    N/G Wt: 4, 932 kgs / 7, 710 kgs

Case 3: 289 x 242 x 274 cm      N/G Wt: 1, 700 kgs / 2, 691 kgs

Case 4: 230 x 162 x 255 cm      N/G Wt: 940 kgs / 1, 571 kgs

Case 5: 384 x 290 x 386 cm      N/G Wt: 4, 826 kgs / 6, 684

Case 6: 319 x 290 x 377 cm      N/G Wt: 4, 507 kgs / 6, 118 kgs

Case 7: 329 x 192 x 192 cm      N/G Wt: 600 kgs / 1, 350 kgs

Case 8: 329 x 192 x 192 cm      N/G Wt: 600 kgs / 1, 350 kgs

Case 9: 230 x 100 x 100 cm      N/G Wt: 700 kgs / 958 kgs

Case 10: 195 x 90 x 82 cm        N/G Wt: 700 kgs / 888 kgs

Case 11: 239 x 172 x 242 cm    N/G Wt: 360 kgs / 1, 007 kgs

Case 12: 179 x 72 x 282 cm      N/G Wt: 500 kgs / 885 kgs

Risk Assessment

A copy of Risk Assessment will be attached

Date / Time of Operation

Est: 10-17/08/2018   –   09:30am

Location of Operation

#### No 51 Seletar Aerospace View

Pratt & Whitney NGPF Manufacturing Company Pte Ltd

Equipment Use

2 x 100 ton mobile crane

Lorry crane

Heavy duty rollers

Wire/webbing sling

Metal sheet/canvas

Shackle

Forklift

1 x boom lift

Obstacles

No obstacle on crane parking area

Barricade operation area to prevent persons who are not involved enter unintentionally

Environment

No lifting operation will be carried out on heavy rain, thunderstorms and lightning weather

All debris will be clear and dispose

Lifting Crew

M.O.M certified lifting supervisor, rigger, signalman and mobile/lorry crane operator will be involved in this operation (attached all lifting crews certificate)

Safety Aspect

All personnel have to ensure that risk control are known and supervisor has to ensure that risk control are in placed                                                                                                                            All our workers are fully equip with standard P.P.E. (safety shoes, safety helmet, safety harness)                                                                                                                                                Lifting machine and lifting gear with M.O.M certificate

Lifting operation are supervise by M.O.M certified lifting supervisor, rigger and signalman

# JOB SCOPE

- Setting up of 2 x 100 ton mobile crane at designated location

- Using 2 x mobile crane to hoist down machine case from container and load onto ground

- Uncrate case

- Hoist up and detach machine from base

- Shift out machine base away using forklift

- Lower down machine slowly

- Insert heavy duty rollers to machine base and secured with bolts and nuts

- Transport machine into production area

- Position machine at the designated location

- Jack up machine, pull out rollers and insert levelling pad under machine bed

- Once job complete, team leader will instruct the team to perform proper housekeeping, all debris will be clear and dispose

- Job complete

Remark:

MOS subject to change by supervisor/lifting supervisor on site

Best Regards

Zailani

Eric Wong Machinery Transportation Pte Ltd

Tel: 62824175